Hello US Embassy

Since the implementation of the project "Connecting Hearts through Code" we accomplished numerous goals that we deliberate to do to come out with a satisfying result until now.
The first two months we had been targeted on developing the website for the project so we could promote our mission through it. We persevered promoting the project the following period and then opened a "call for application" where we have been so impressed by the number of the women that have been so excited to be part of code4mitrovica.
And also we would mention that we used a few money into the budget line of the Contractual prices quantity 4 Accounting services to promote/boost the video of the project and also the application form so we used seventy-seven euro from 401.76 in total.
After the promoting period, we additionally selected 10 girls from North Mitrovica (Serbian) and 10 women from South Mitrovica (Albanian) we have been so satisfied that there was a massive aim to apply for this assignment. All of the selected women confirmed the participation.
We also are informing you that besides the 3 Albanian mentors we found out that we need also a translator Albanian-Serbian English-Serbian so the Serbian women would not feel uncomfortable all through the training. Due to the fact, a lot of them could not communicate and understand the English language. But we did not plan that before so we don't have a planned budget for this.
Consequently, we thought, using the money that will be left from the mentors budget and pay the translator. And of course, we are requesting your permission to continue with this plan.
The training is going to place in IBCM (international business college Mitrovica) Mitrovica North on weekends from 10:00 to 16:00.